## Sheet1
CSI4142 Physical Design and Data Staging - Project Planning
Deliverable | Team member(s) responsible | Expected completion date | Actual completion date | Estimate time (hours) to complete | Actual time (hours) to complete | Notes (if any)
Create database instance and tables | Heng (Scott) Zhang ,Xia (Cynthia) Sheng, Xinyu Ji | 2021-02-19 | 2021-02-18 | 2 | 1h45min
Staging of Date dimension | Heng (Scott) Zhang | 2021-02-20 | 2021-02-19 | 0.5 | 0.5
Staging of Patient dimension | Heng (Scott) Zhang | 2021-02-20 | 2021-02-19 | 1 | 45min
Staging of PHU dimension | Xinyu Ji | 2021-02-20 | 2021-02-19 | 0.5 | 0.5
Staging of Mobility dimension | Heng (Scott) Zhang | 2021-02-20 | 2021-02-19 | 1 | 0.5
Staging of Weather dimension | Xia (Cynthia) Sheng | 2021-02-21 | 2021-02-19 | 1 | 45min
Map PHU, Mobility and Weather dimensions | Heng (Scott) Zhang | 2021-02-25 | 2021-02-19 | 2 | 1h45min
Staging of Special Measures dimension | Xinyu Ji | 2021-02-20 | 2021-02-19 | 0.5 | 0.5
Surrogate key pipeline – including role-playing dates | Xia (Cynthia) Sheng | 2021-02-28 | 2021-02-19 | 2 | 1h45min
Staging of fact table – including FKs and measures | Heng (Scott) Zhang ,Xia (Cynthia) Sheng | 2021-02-28 | 2021-02-19 | 2 | 1h45min
Data quality handling and reporting | Xinyu Ji | 2021-03-01 | 2021-02-19 | 1 | 1
Others - if any